## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (Object Tracking in Surveillance Videos) | MUST HAVE | No Dependency | Prashant Singh | 3- Completed
S1 | S1 | US-002 | Image processing using OpenCV | MUST HAVE | opencv, pandas, matplotlib, imageAI | Prashant Singh | 3- Completed
S2 | S2 | US-003 | Object detection using tiny yolo | MUST HAVE | tiny-yolov3.pt model, torchvision, torchaudio | Prashant Singh | 3- Completed
S3 | S3 | US-004 | Object Tracking | MUST HAVE | yolov4.cfg, yolov4.weights, classes.txt | Prashant Singh | 3- Completed
S4 | S4 | US-005 | Dense optical flow | MUST HAVE | matplotlib, opencv | Prashant Singh | 3- Completed
S5 | S5 | US-006 | Sparse option flow | MUST HAVE | numpy, opencv | Prashant Singh | 3- Completed
S6 | S6 | US-007 | Document Discussion (Agile Template) | MUST HAVE | No Dependency | Prashant Singh | 3- Completed
S6 | S6 | US-008 | Image processing using OpenCV U.I. Implementation | MUST HAVE | opencv, pandas, matplotlib, imageAI, streamlit | Prashant Singh | 3- Completed
S7 | S7 | US-009 | Object detection using tiny yolo U.I. Implementation | MUST HAVE | tiny-yolov3.pt model, torchvision, torchaudio, streamlit | Prashant Singh | 3- Completed
S8 | S8 | US-010 | Object Tracking U.I. Implementation | MUST HAVE | yolov4.cfg, yolov4.weights, classes.txt, streamlit | Prashant Singh | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 15 | 10 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project (Object Tracking in Surveillance Videos) | 2024-12-04 | 2024-12-06 |  | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Image processing using OpenCV | 2024-12-07 | 2024-12-08 |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Object detection using tiny yolo | 2024-12-11 | 2024-12-11 |  | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Object Tracking (DNN module) | 2024-12-12 | 2024-12-15 |  | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | Dense optical flow | 2024-12-16 | 2024-12-22 |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | Sparse optical flow | 2024-12-23 | 2024-12-29 |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | Document Discussion (Agile Template) | 2025-01-02 | 2025-01-06 |  | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | Image processing using OpenCV U.I. Implementation | 2025-01-09 | 2025-01-13 |  | Build | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-09 | Object detection using tiny yolo U.I. Implementation | 2025-01-16 | 2025-01-20 |  | Build | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-10 | Object Tracking (DNN module) U.I. Implementation | 2025-01-23 | 2025-01-27 |  | Build | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Asked for notes on AI and tools | Conducted a detailed discussion with the mentor
Sprint 1 | Day 4 | Query on Opencv and tensorflow topic | Conducted a session and reviewed the project requirements
Sprint 2 | Day 7 | Confusion on Object Detection | Conducted additional research and explained the code step by step.
Sprint 2 | Day 9 | Query on Object Tracking | Created a code to explain the use of modules on the tracking code.
Sprint 3 | Day 12 | Query on Implementation of U.I | Mentor explained on how to create U.I and gave ideas about the different tools
Sprint 4 | Day 16 | Doubts in the implementation | Conducted a session and reviewed the U.I Implementation
Sprint 5 | Day 23 | Query on the final project | Provided solutions for the issue and explained the process to solve it
Sprint 6 | Day 27 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-04 | 2024-12-08 | Harpreet Singh | Regularly reviewing documentation | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 3 | 2024-12-16 | 2024-12-22 | Harpreet Singh | Focusing on Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python coding completion on time
3 | Sprint 4 | 2024-12-23 | 2024-12-29 | Harpreet Singh | Getting ready for project implementation | Rushing through understanding concepts. | Asking for help when stuck. | Completed all the tasks with support from the team
4 | sprint 5 | 2025-01-02 | 2025-01-16 | Harpreet Singh | Engaging in project discussions | Delaying U.I Implementation | Collaborating on language processing strategies & modules for U.I building | Completed U.I Implementation properly and received team feedback for improvements.